## Compliance Matrix
Bid Desk — Compliance Matrix — PRD B290 Roof — Pine Ridge Job Corps CCC — Solicitation 12441926Q0048 (no amendments posted as of Oct 4, 2026)
Prepared Oct 4, 2026 from public SAM.gov documents. Page numbers = physical page of the PDF as posted on SAM.gov. Not legal advice; verify against the full solicitation.
# | Requirement | Type | Source document | Section / clause | PDF page(s) | How to meet | Owner | Status
1 | Active SAM entity registration to submit an offer / at time proposals are due | Mandatory (eligibility) | 12441926Q0048.pdf | AGAR 452.215-71(a)(2) | 19 | Verify SAM active, 'All Awards', NAICS 238160 listed. |  | Open
2 | Signed SF-1442 (items 14–20) incl. amendment acknowledgment | Mandatory | 12441926Q0048.pdf | SF-1442; 452.215-71(c)(i) | 22 | Complete blocks 14–20; acknowledge any amendment issued before Oct 20. |  | Open
3 | Offer acceptance period ≥180 calendar days | Mandatory | 12441926Q0048.pdf | SF-1442 item 13d | 1 | Enter 180 (or more) in item 17. |  | Open
4 | Bid guarantee required (offer guarantee 'is' required; listed in required items) | Mandatory (clarify) | 12441926Q0048.pdf | SF-1442 13b; 452.215-71(c)(v) | 22 | Obtain bid bond (SF-24) from a T-listed surety; ask CO the amount since 52.228-1 is unchecked. |  | Open
5 | Payment & performance bonds within 10 calendar days after award | Mandatory (post-award) | 12441926Q0048.pdf | SF-1442 12a/12b; cover note | 1 | Pre-qualify with surety now (SF-25/25A). |  | Open
6 | Proposal in 2 volumes: Vol I Technical Approach (unlimited) + Demonstrated Prior Experience (max 5 pages); Vol II Price | Mandatory (format) | 12441926Q0048.pdf | 452.215-71(a) table | 19 | Separate files; label volumes; keep Factor 2 to ≤5 pages. |  | Open
7 | Font ≥12-pt Times New Roman; tables ≥8-pt; 1-inch margins; pages over limit not read | Mandatory (format) | 12441926Q0048.pdf | 452.215-71(a) | 19 | Apply a Word template with these settings. |  | Open
8 | Files must be MS Word, Excel or Adobe PDF | Mandatory (format) | 12441926Q0048.pdf | 452.215-71(a)(1) | 19 | PDF for volumes; native .xlsx for SOI. |  | Open
9 | Technical approach: how you'll execute drawings/specs/SOI; plan, manage, control | Evaluation (Factor 1) | 12441926Q0048.pdf | Technical Approach (Project Schedule) | 16 | Narrative by spec section: demo, flute fill, insulation, PVC, gutters, vents, inspections. |  | Open
10 | CPM schedule: all activities, resources, durations, logic links, critical path, total float | Evaluation (Factor 1) | 12441926Q0048.pdf | Factor 1 criteria | 16 | Build in MS Project/GanttProject; show submittal review (12 days), bonds, NTP, 90-day completion. |  | Open
11 | Identify subcontractor tasks + company names + their capabilities | Mandatory (Factor 1) | 12441926Q0048.pdf | 452.215-71(b) Factor 1 | 20 | Name sheet-metal/gutter or electrical subs if used. |  | Open
12 | ≥3 recent & relevant projects (last 5 years) with description, $, year, owner contact; ≥1 year experience | Mandatory (Factor 2) | 12441926Q0048.pdf | 452.215-71(b) Factor 2 | 21 | Choose PVC/single-ply or metal-retrofit jobs; include phone and e-mail. |  | Open
13 | Past performance: Acceptable or Neutral (CPARS/other sources may be used) | Evaluation | 12441926Q0048.pdf | Demonstrated Prior Experience | 17 | Check your CPARS/FAPIIS; resolve any negative records. |  | Open
14 | Price on Attachment 3 SOI, column E, Excel with formulas unlocked; all items priced | Mandatory (price) | 12441926Q0048.pdf | 452.215-71(b) Vol II; (c)(ii) | 22 | Enter lump sum in E4 of 'CONTRACT (NO OPTIONS)' tab. |  | Open
15 | Price narrative + backup sufficient for reasonableness; progress payment schedule if applicable; sub price analysis | Mandatory (price) | 12441926Q0048.pdf | 452.215-71(b) Vol II | 21 | Attach cost breakdown (labor, material, equipment, bonds, OH&P) + sub quotes. |  | Open
16 | Inconsistency: price instructions mention tabs (Water, Sewer, Lift Stations, Campground…) not present in SOI | Clarify | 12441926Q0048.pdf | 452.215-71(b) Vol II | 21 | Ask CO by Oct 8; meanwhile price only the single LS item. |  | Open
17 | Offer by e-mail to nicholas.zane@usda.gov by Oct 20, 2026 17:00 EST; offeror must confirm receipt | Mandatory (submission) | 12441926Q0048.pdf | Instructions p.23 | 23 | Send by Oct 19; split attachments if large; request confirmation. |  | Open
18 | Questions in writing by Oct 8, 2026 17:00 EST, solicitation name/number in subject | Deadline | 12441926Q0048.pdf | Questions | 23 | One consolidated e-mail; cc Aaron Sanford. |  | Open
19 | Scope: remove/replace gutters; PVC metal-retrofit over-roof (polyiso flute fill + continuous insulation + PVC membrane), Class A/B/C fire rating, wind pressure | Scope | Attachment 2 - PRD B290 Roof Specs.pdf | 010150 §1.1 | 2 | Price per drawings; transition to existing canopy/storage roofs. |  | Open
20 | Approx. 7,800 sq ft horizontal roof area; 5,845 GSF interior; ground snow load 40 psf | Scope (reference) | Attachment 1 - PRD B290 Roof Drawings.pdf | Building information | 5,6 | Field-verify; base takeoff on drawing A1.0. |  | Open
21 | Basis of design: Duro-Last 'Metal Retrofit'; substitutions must meet/exceed all salient features | Technical | Attachment 2 - PRD B290 Roof Specs.pdf | 010150 §1.1 | 2,27,28 | Use BOD or submit equal with comparison sheet. |  | Open
22 | Installer approved/authorized/licensed by manufacturer and eligible for special warranty | Mandatory (qualification) | Attachment 2 - PRD B290 Roof Specs.pdf | 075419 §1.5 | 26 | Get a manufacturer letter confirming installer status. |  | Open
23 | 20-year NDL manufacturer special warranty from substantial completion | Mandatory (deliverable) | Attachment 2 - PRD B290 Roof Specs.pdf | 075419 §1.6 | 26 | Include manufacturer inspection fees in price. |  | Open
24 | Fastener pull-out tests per manufacturer; verify metal profile/flatness | Technical | Attachment 2 - PRD B290 Roof Specs.pdf | 075419 §3.2 | 29 | Schedule tests before insulation install. |  | Open
25 | Energy Star roofing (sustainable products) | Technical | Attachment 4 - Sustainable Products.pdf | Attachment 4 | 1 | Select an Energy Star-listed PVC membrane. |  | Open
26 | Start within 10 days after NTP; complete within 90 calendar days incl. cleanup | Performance | 12441926Q0048.pdf | SF-1442 item 11; Period of Performance | 14 | Plan crews/material lead times; weather contingency. |  | Open
27 | Work hours 8:00 AM–4:30 PM Mon–Fri; government occupies site | Performance | Attachment 2 - PRD B290 Roof Specs.pdf | 010150 §1.3–1.4 | 2 | Price no overtime unless approved. |  | Open
28 | Licensed journeyman electricians/plumbers (state of performance) where applicable | Mandatory (if applicable) | Attachment 2 - PRD B290 Roof Specs.pdf | 010150 §1.9 | 5 | Use Nebraska-licensed trades for vent/gas work. |  | Open
29 | Pre-construction conference within 10 days of award; bonds & insurance accepted before NTP | Post-award | Attachment 2 - PRD B290 Roof Specs.pdf | 010150 §2.1 | 5,6 | Have insurance certificates ready at award. |  | Open
30 | Submittals: Accident Prevention Plan, construction schedule, licenses/certifications; action submittals 12 days after NTP | Post-award deliverable | Attachment 2 - PRD B290 Roof Specs.pdf | 010150 §3.4 | 8 | Prepare APP and product data package in advance. |  | Open
31 | Weekly progress reports with annotated photos; substantial completion and punch-list reports | Post-award deliverable | Attachment 2 - PRD B290 Roof Specs.pdf | 010150 §3.5 | 8 | Assign a superintendent (FAR 52.236-6) to report. |  | Open
32 | One-year warranty on entire project (FAR 52.246-21) + project record documents | Closeout | Attachment 2 - PRD B290 Roof Specs.pdf | 010150 §3.6 | 8 | Include in closeout package. |  | Open
33 | Construction Wage Rate Requirements (Davis-Bacon), payrolls; price adjustment actual method | Mandatory (labor) | 12441926Q0048.pdf | FAR 52.222-6/-8; 52.222-32 | 8 | Price labor at or above Att. 5 WD rates (scanned image; rates not extracted by Bid Desk). |  | Open
34 | AGAR 452.203-71 anti-discrimination / DEI compliance certification (flowdown to subs) | Mandatory (certification) | 12441926Q0048.pdf | AGAR 452.203-71 | 9 | Review with counsel; flow down to subcontracts. |  | Open

## Sources
Document | Where
12441926Q0048.pdf | SAM.gov notice attachments
Attachment 2 - PRD B290 Roof Specs.pdf | SAM.gov notice attachments
Attachment 1 - PRD B290 Roof Drawings.pdf | SAM.gov notice attachments
Attachment 3 - PRD B290 Roof SOI.xlsx | SAM.gov notice attachments
Attachment 4 - Sustainable Products.pdf | SAM.gov notice attachments
Attachment 5 - Wage Determination Rates.pdf | SAM.gov notice attachments
Link | https://sam.gov/opp/7aa6a57795f2466d8340b29974830568/view

## Disclaimer
Disclaimer. Sample prepared by Bid Desk from public SAM.gov documents and USAspending data retrieved Oct 4, 2026. Not legal, accounting or contracting advice. No guarantee of award. Estimates are marked as such and must be validated. The offeror is solely responsible for reading the full solicitation and all amendments and for the accuracy of every representation it submits (knowingly false statements may create liability under the False Claims Act). Always confirm requirements with the Contracting Officer in writing.