## Compliance Matrix
Bid Desk — Compliance Matrix — IDIQ Tree Maintenance Services, Beaver Project Office — Solicitation W9127S26QA051 (incl. Amendment 0001, 24 Sep 2026)
Prepared Oct 4, 2026 from public SAM.gov documents. Page numbers = physical page of the PDF as posted on SAM.gov. Not legal advice; verify against the full solicitation.
# | Requirement | Type | Source document | Section / clause | PDF page(s) | How to meet | Owner | Status
1 | Active SAM registration set to 'All Awards' at time of quote submission, or ineligible | Mandatory (eligibility) | Amendment 0001.pdf | Mandatory SAM account (RFO 4.203-1(b)) | 4 | Check SAM status and purpose of registration = All Awards. |  | Open
2 | Quotes only by e-mail, PDF format, to brandee.m.wright@usace.army.mil; solicitation number in subject | Mandatory (submission) | Amendment 0001.pdf | Instructions | 3 | One merged PDF; subject 'W9127S26QA051 – [Company]'. |  | Open
3 | Due Wednesday Oct 14, 2026, 10:00 AM CDT | Deadline | Amendment 0001.pdf | Instructions | 3 | Send by Oct 13; confirm receipt by phone/e-mail. |  | Open
4 | Required doc 1: RFQ cover page signed (name, address, phone, e-mail, POC, TIN, UEI, CAGE) | Mandatory | Amendment 0001.pdf | Required Documents #1; cover page | 3,5 | Fill every field; sign and date. |  | Open
5 | Required doc 2: completed provisions as applicable (Section K fill-ins, e.g., 52.209-5 responsibility matters) | Mandatory | Amendment 0001.pdf | Required Documents #2; Section K | 3 | Complete every [ ] fill-in in Section K. |  | Open
6 | Required doc 3: pricing schedule with unit and total prices, all 12 CLINs for base + 4 options | Mandatory (price) | Amendment 0001.pdf | Pricing Schedule; Factor 5 | 6 | Fill 60 unit prices; totals per period; grand total = evaluated price. |  | Open
7 | Required doc 4: technical submission IAW 52.212-2 | Mandatory | Amendment 0001.pdf | Required Documents #4 | 3 | Organize by Factors 1–4 with headings that mirror the RFQ. |  | Open
8 | Required doc 5: signed amendments (Amendment 0001) | Mandatory | Amendment 0001.pdf | SF-30 block 11/15 | 1 | Sign SF-30 blocks 15A–C and include it in the PDF. |  | Open
9 | Award: lowest total evaluated price (base + all options) among quotes Acceptable on all non-price factors; factors not traded off | Evaluation basis | Amendment 0001.pdf | 52.212-2 (Section M) | 43 | Price sharply; pass/fail technical means no extra credit for extras. |  | Open
10 | Factor 1: max 3 recent (≤6 yrs) relevant contracts as prime or sub with contract no./type, customer, PoP, $ value | Evaluation (F1) | Amendment 0001.pdf | Factor 1 A.4 | 44 | Use tree removal/pruning/storm-cleanup contracts on public land if possible. |  | Open
11 | For each reference: POC (name, title, e-mail, phone of CO/COR/PM) + work narrative + performance/safety narrative (EM 385-1-1/OSHA) | Evaluation (F1) | Amendment 0001.pdf | Factor 1 A.5–A.7 | 44 | Confirm POCs will answer; describe safety record (EMR, OSHA logs). |  | Open
12 | Optional: PPQs or CPARS evaluations | Optional (F1) | Amendment 0001.pdf | Factor 1 Additional Information | 45 | Attach any CPARS; ask a client to fill a PPQ. |  | Open
13 | No relevant record → Neutral rating (allowed) | Evaluation (F1) | Amendment 0001.pdf | Section M ratings | 43,52 | New firms can still be acceptable on F1. |  | Open
14 | Factor 2: QC Manager & Alternate resumes, ≥3 yrs supervisory experience in tree/forestry/grounds; full authority statement | Mandatory (F2) | Amendment 0001.pdf | Factor 2 #11; PWS 1.7.2 | 46 | Two resumes + signed authority letter. |  | Open
15 | Crew minimum 3 per operational unit: foreman (≥2 yrs leading tree crews), climber, groundman | Mandatory (F2) | Amendment 0001.pdf | Factor 2 #12 | 47 | Org chart + resumes/training records per role. |  | Open
16 | ≥2 crew members per active crew with current First Aid & CPR | Mandatory (F2) | Amendment 0001.pdf | Factor 2 #13; PWS 1.10.5 | 47 | Attach card copies with expiration dates. |  | Open
17 | Security & vetting statement: USACE SWL Security Level II, E-Verify, OF-306 / SWL Form 487 | Mandatory (F2) | Amendment 0001.pdf | Factor 2 #14 | 47 | Signed statement; enroll in E-Verify if not already. |  | Open
18 | Factor 3: equipment list with make, model, year, condition, ownership and specs | Mandatory (F3) | Amendment 0001.pdf | Factor 3 A | 48 | Table per category; attach spec sheets/photos. |  | Open
19 | Bucket truck/aerial lift: pneumatic tires, ≥300 lb bucket capacity, ≥60-ft working height, hydraulic outriggers | Mandatory (F3) | Amendment 0001.pdf | Factor 3 table; PWS 4.4.3 & 5.2.5 | 48 | Attach manufacturer spec sheet showing working height. |  | Open
20 | Skid-steer or mini-excavator ≥7,000 lb operating weight for heavy logs/debris | Mandatory (F3) | Amendment 0001.pdf | Factor 3 table; PWS 4.4.1 | 48 | State operating weight from spec sheet. |  | Open
21 | Heavy-duty trailers or box trucks dedicated to off-site debris hauling | Mandatory (F3) | Amendment 0001.pdf | Factor 3 table; PWS 4.4.2 | 49 | List capacity (cu yd / GVWR). |  | Open
22 | Commercial stump grinder able to grind ≥4 in below natural grade | Mandatory (F3) | Amendment 0001.pdf | Factor 3 table; PWS 5.2.4 | 45,49,67 | Spec sheet showing cutting depth. |  | Open
23 | Chainsaws, pole saws, commercial chipper, traffic barricades, signs, PPE per EM 385-1-1 | Mandatory (F3) | Amendment 0001.pdf | Factor 3 table; PWS 1.10.1, 5.1.3, 5.2.6 | 49 | List quantities. |  | Open
24 | Factor 4: response time plan: emergency on site with crew & equipment ≤4 h, 24/7/365 | Mandatory (F4) | Amendment 0001.pdf | Factor 4; PWS 1.4.1 | 50 | Show base address, drive times (Attachment 6 mileage), on-call roster. |  | Open
25 | Normal service call on site ≤24 h during 7:00–17:00 Mon–Fri | Mandatory (F4) | Amendment 0001.pdf | Factor 4 | 50 | Describe dispatch process and backup crew. |  | Open
26 | IDIQ minimum guarantee $5,000 (base only) stated in RFQ, but Amendment 0001 says guaranteed-minimum language was removed from PWS 1.3 | Clarify | Amendment 0001.pdf | Minimum Guarantee; SF-30 block 14 | 3 | Ask CO in writing; don't price assuming any minimum. |  | Open
27 | Quantities are estimates; Government may self-perform; orders only by written Delivery Order from KO | Contract term | Amendment 0001.pdf | PWS 1.3–1.4, 1.12 | 54 | Price each CLIN to be profitable on its own. |  | Open
28 | Insurance: CGL bodily injury ≥$500,000/occurrence; auto ≥$200k/person, $500k/occurrence BI, $20k PD | Mandatory (post-award) | Amendment 0001.pdf | PWS 1.11 | 61 | Get broker confirmation now; proof due within 14 days of award. |  | Open
29 | Quality Control Plan within 2 weeks of award; daily QC inspections/reports | Post-award deliverable | Amendment 0001.pdf | PWS 1.7 | 56 | Use Attachment 4 example outline. |  | Open
30 | Within 14 days of award: Accident Prevention Plan, proof of insurance, QCP, AHA, employee list, QC rep in writing | Post-award deliverable | Amendment 0001.pdf | Attachment 2 Deliverables | 60,72 | Draft the Accident Prevention Plan to EM 385-1-1 in advance. |  | Open
31 | Monthly exposure-hours report (1st workday of month) | Post-award deliverable | Amendment 0001.pdf | Attachment 2 | 72 | Track man-hours per delivery order. |  | Open
32 | Work hours 7:00 AM–5:00 PM Mon–Fri except holidays (emergencies excepted) | Performance | Amendment 0001.pdf | PWS 1.8.2 | 58 | Plan crew calendar; price emergency CLIN for after-hours. |  | Open
33 | Service Contract Labor Standards apply; WD 2015-5109 Rev 32 (Benton/Madison/Washington) and WD 2015-5723 (Carroll/Newton) attached as scanned pages | Mandatory (labor) | Amendment 0001.pdf | 52.222-41; WD pages 91–104 | 12 | Read tree trimmer/laborer rates from the scanned WDs; pay at least WD + H&W. |  | Open
34 | Limitations on subcontracting (FAR 52.219-14) apply | Mandatory | Amendment 0001.pdf | 52.219-14 | 18,20 | Do not pay more than 50% of the services amount to non-similarly-situated subcontractors. |  | Open

## Sources
Document | Where
Amendment 0001.pdf | SAM.gov notice attachments
Combined Synopsis Solicitation.pdf | SAM.gov notice attachments
Link | https://sam.gov/opp/89248642cff04db89a0af5c571ab337e/view
Link | https://www.usaspending.gov/award/CONT_IDV_W9127S22D0027_9700
Link | https://www.usaspending.gov/award/CONT_IDV_W9127S26DA001_9700

## Disclaimer
Disclaimer. Sample prepared by Bid Desk from public SAM.gov documents and USAspending data retrieved Oct 4, 2026. Not legal, accounting or contracting advice. No guarantee of award. Estimates are marked as such and must be validated. The offeror is solely responsible for reading the full solicitation and all amendments and for the accuracy of every representation it submits (knowingly false statements may create liability under the False Claims Act). Always confirm requirements with the Contracting Officer in writing.